PROBATIONARY PERIOD  ·  WORK SUMMARY

Establishing a Research Program in Computational Protein–Protein Interaction

A Multimodal Deep-Learning Framework for Predicting Protein–Protein Interactions and Their Drug-Relevant Properties

| Name | Dr. Khalid Zaman |
| --- | --- |
| Position | Research Assistant Professor (RAP) |
| Institution | SUAT [confirm full institution name] |
| Supervisor | Prof. Zhaoxi Sun |
| Probationary period | 6 months ([start date] – [end date]) |
| Report date | [date] |
| Research area | Multimodal deep learning for protein–protein interaction |

Highlights at a glance ▸ Reproduced a state-of-the-art PPI baseline end-to-end — AUPR 0.917 on the D-SCRIPT human benchmark, versus ~0.55–0.61 for earlier sequence methods. ▸ Designed and trained an original model (CrossAttnPPI) that exceeds the published leakage-free benchmark — AUPR 0.709 vs ~0.69 prior state of the art. ▸ Architected and implemented a novel multimodal, multi-task model fusing sequence, structure, and evolution — every component unit-tested. ▸ Built a fully reproducible HPC research pipeline — SLURM cluster, version-controlled and mirrored to two remote repositories.

1.  Executive Summary

During my probationary period I established and substantially advanced an independent, well-scoped research program in computational structural biology: the design of a multimodal deep-learning framework for predicting protein–protein interactions (PPIs) and their drug-relevant properties. Within six months the work progressed from a bare compute environment to a trained model that exceeds the published state of the art on a rigorous, leakage-free benchmark, with a novel multimodal extension now in active development.

The project is engineered for scientific rigour and reproducibility. Every phase concludes in a self-contained, reportable result; all code and documentation are version-controlled and mirrored across the group's GPU cluster and two independent remote repositories. In parallel with the core research, I contributed to [the environment/compute set-up, proposal development, student mentoring, and group collaboration — add your specifics in Section 5].

2.  Research Project — Overview

From the amino-acid sequences of two proteins, the target model predicts (1) whether they interact, (2) how strongly they bind, and (3) which residues form the interface — each with residue-level interpretability. It combines three complementary views of each protein: a protein language model (sequence), an experimentally grounded structural module (PDBbind complex structures as residue contact graphs), and an evolutionary module (conservation from multiple sequence alignments), reasoned across the pair by a cross-attention engine. The work is deliberately complementary to the group's bound-structure prediction methods rather than competing with them.

The project follows a disciplined, phased plan. Progress to date:

| Phase | Focus | Status | Outcome |
| --- | --- | --- | --- |
| 0 | Environment & baseline | DONE | Built the GPU/deep-learning environment; reproduced the PLM-interact baseline end-to-end (AUROC 0.989 / AUPR 0.917). |
| 1 | Data assembly | DONE | Assembled ~274k interaction pairs (Bernett gold standard), 8,207 affinity complexes (PPB-Affinity/PDBbind), and interface-residue labels. |
| 2 | Core interaction model | DONE | Built & trained CrossAttnPPI (ESM-2 + cross-attention); best model AUROC 0.717 / AUPR 0.709, above published SOTA (~0.69). |
| 3 | Structural + evolutionary modules | IN PROGRESS | Implemented contact-graph and MSA-conservation modules and a multi-task model; UniRef50 + MMseqs2 alignment pipeline running. |
| 4 | Affinity & interface heads | PLANNED | Binding-affinity (pKd) and interface-residue prediction, trained on the prepared structural data. |
| 5 | Benchmarking & ablations | PLANNED | Full comparison against baselines and ablation of each modality. |
| 6 | Dissemination | PLANNED | Manuscript and open-source code + model release. |

3.  Key Results

All figures are on large, held-out test sets that were never seen during training.

| Model | Benchmark (held-out) | AUROC | AUPR | Note |
| --- | --- | --- | --- | --- |
| PLM-interact-650M (reproduced) | D-SCRIPT human (52,725 pairs) | 0.9885 | 0.9174 | vs ~0.55 (D-SCRIPT), ~0.58 (Topsy-Turvy) |
| CrossAttnPPI-35M (ours) | Bernett gold (52,048 pairs) | 0.7033 | 0.7017 | above published baseline |
| CrossAttnPPI-650M (ours) | Bernett gold (52,048 pairs) | 0.7174 | 0.7093 | best — exceeds SOTA (~0.69 AUPR) |

Two results are especially notable. First, the Phase 0 reproduction confirmed a fully working, credible pipeline (AUPR 0.917 against ~0.55–0.61 for prior sequence methods). Second — and more importantly — the original model built in-house exceeds the published state of the art on the deliberately hard, leakage-free Bernett benchmark (AUPR 0.709 vs ~0.69), with test performance matching validation on 52,048 pairs, indicating trustworthy, non-overfit results.

4.  Research Infrastructure & Reproducibility

- Compute environment: built and validated a modern deep-learning stack (PyTorch 2.7.1 / CUDA 12.8) on the group's RTX 50-series GPU cluster, with jobs orchestrated through the SLURM scheduler.

- Version control & backup: the full codebase is under Git and mirrored to both Gitee and GitHub, kept in continuous sync across the cluster and laptop, so no work can be lost.

- Documentation: a single source-of-truth project record, per-phase technical summaries, and dataset documentation keep the project auditable and easy to hand over or resume.

- Reproducibility: each phase is a self-contained, re-runnable unit; data-preparation and training are fully scripted.

5.  Broader Contributions & Responsibilities

Beyond the core research, my probationary contributions include the following. (Please expand each point with concrete specifics — names, dates, numbers):

- Research proposal: authored the full project proposal (v10), refining scope, aims, and methodology in consultation with the supervisor.

- Environment & data engineering: independently set up the compute environment and assembled all public datasets required for the project.

- [Student mentoring / supervision — e.g., guided N postgraduate students on ...]

- [Group collaboration — e.g., contributed to shared methods / discussions with the DATUM-FACET / docking team on ...]

- [Teaching / seminars — e.g., delivered a group seminar on protein language models on (date)]

- [Service / other duties — add any additional responsibilities here]

6.  Skills & Competencies Demonstrated

- Deep learning: PyTorch, Transformers, protein language models (ESM-2), graph neural networks, cross-attention, and multi-task learning.

- Computational biology: PPI datasets, PDBbind/RCSB structural data, interface derivation, and MSA generation (MMseqs2, UniRef50).

- High-performance computing: SLURM job design, GPU training, and large-scale data handling.

- Reproducible research & scientific writing: Git-based workflows, structured documentation, and proposal/report preparation.

7.  Plans for the Coming Period

- Complete Phase 3: finish the multiple-sequence-alignment pipeline and train the multimodal model on the reserved training GPU.

- Phase 4: add and evaluate the binding-affinity and interface-residue prediction heads.

- Phase 5: run full benchmarking and modality-ablation studies to quantify the contribution of structure and evolution.

- Phase 6: prepare a manuscript for publication and release the code and trained models openly.

- [Any broader goals for the next period — grants, collaborations, teaching]

8.  Conclusion

In six months this work has moved from environment set-up to a trained, benchmark-exceeding model and a working multimodal architecture, on a rigorous and fully reproducible foundation. The trajectory is strong and the remaining phases are well-defined. I am confident this establishes a solid basis for a productive and impactful research program, and I look forward to carrying it through to publication.

| _______________________________ Dr. Khalid Zaman Research Assistant Professor | _______________________________ Prof. Zhaoxi Sun (Supervisor) Date: [ ] |
| --- | --- |